## 45-Day Checklist
iNeuBytes • 45-Day Web Development Internship - Intern Checklist
Course ID: WBINB20726 ¦ Program: Virtual iNeuBytes Internship Program (VIIP) ¦ Mentor: Mayank Kumar (IIT Dhanbad) - Full-stack Web Developer
Intern Name: ______________________ Regd No: ______________ Start Date: ____________ Repo/Doc Name Format: InternFirstName_RegdNo_iNeuBytes
PROGRESS |  |  | 0 of 78 done (0% complete) ¦ In Progress: 0 ¦ Blocked: 0
# | Phase | Task / Deliverable | Details | Target Day | Status | Notes
1 | 0 · Onboarding & Setup | Read the full program deck | Understand all tasks, submission rules, and mentor expectations (Course ID WBINB20726) | 1 | Not Started
2 |  | Set up dev environment | Code editor, browser, Git; Node.js or PHP + relational database for the Major Project | 1 | Not Started
3 |  | Create public GitHub repository | Name it exactly: InternFirstName_RegdNo_iNeuBytes - keep it PUBLIC | 1 | Not Started
4 |  | Create task folders in repo | Separate folders: Task 1, Task 2, Task 3, Major Project | 1 | Not Started
5 |  | Create Google Doc report | Title it: InternFirstName_RegdNo_iNeuBytes | 1 | Not Started
6 |  | Add identity to README & Doc | Name, Regd No., and Course ID on README file and Google Doc main page | 1 | Not Started
7 | 1 · Task 1 - Healthcare / Clinic Landing Page | HTML: responsive home page | Semantic HTML; separate section for each component | 2-3 | Not Started
8 |  | Navigation bar + Hero with CTA | Responsive nav; hero section with call-to-action button | 2-3 | Not Started
9 |  | About the Clinic section | Intro / overview of the clinic | 3 | Not Started
10 |  | Medical Services section | List of services offered | 3 | Not Started
11 |  | Why Choose Us section | Key differentiators / highlights | 4 | Not Started
12 |  | Doctor Highlights | Featured doctors with cards | 4 | Not Started
13 |  | Patient Testimonials | Reviews / feedback block | 4 | Not Started
14 |  | Appointment Enquiry Form | Fields: Patient Name, Email, Phone, Preferred Department, Message Box | 5 | Not Started
15 |  | Contact Info + Google Maps | Contact details with embedded Google Maps | 5 | Not Started
16 |  | Footer | Links, contact, social | 5 | Not Started
17 |  | CSS: professional healthcare theme | Style nav, buttons, cards, forms; hover effects and animations | 6 | Not Started
18 |  | JS: form validation + smooth scrolling | Client-side validation on the enquiry form; smooth scroll | 6 | Not Started
19 |  | JS: responsive nav + interactive UI | Mobile menu toggle, interactive components | 6 | Not Started
20 |  | Responsive design check | Mobile, tablet, desktop friendly; smooth navigation; attractive UI | 7 | Not Started
21 |  | Test & debug | Validate forms, browser compatibility, fix layout issues | 7 | Not Started
22 |  | Push Task 1 to GitHub | Commit into the Task 1 folder | 8 | Not Started
23 |  | Write Task 1 development report | Document approach and results in the Google Doc | 8 | Not Started
24 |  | Record demo video | Showcase the landing page and its responsiveness | 8 | Not Started
25 | 2 · Task 2 - Doctor Appointment Booking System | HTML: Home page | Landing / entry page | 9 | Not Started
26 |  | HTML: Doctor Listing page | Grid/list of doctors | 9-10 | Not Started
27 |  | HTML: Doctor Details / Profile page | Name, Department, Experience, Available Time Slots, Consultation Fee | 10 | Not Started
28 |  | HTML: Appointment Booking form | Select Doctor, Select Date, Select Time Slot, Patient Details, Book | 11 | Not Started
29 |  | HTML: Confirmation & Summary/History | Appointment confirmation + appointment summary (frontend) | 11 | Not Started
30 |  | CSS: responsive layout & cards | Doctor profile cards, booking forms, buttons, nav - professional theme | 12 | Not Started
31 |  | JS: doctor search & department filter | Search by name; filter by department | 13 | Not Started
32 |  | JS: appointment booking + validation | Booking flow, form validation, dynamic appointment summary | 13-14 | Not Started
33 |  | JS: local storage (optional) | Persist appointments on the frontend | 14 | Not Started
34 |  | Test & debug | Booking workflow, responsiveness, search/filters, forms, cross-browser | 15 | Not Started
35 |  | Push Task 2 to GitHub | Commit into the Task 2 folder | 16 | Not Started
36 |  | Write Task 2 development report | Detailed write-up in the Google Doc | 16 | Not Started
37 |  | Record demo video | Project demonstration walkthrough | 16 | Not Started
38 | 3 · Task 3 - Healthcare Management Dashboard | HTML: Dashboard shell | Dashboard Home, sidebar navigation, top navigation bar, user profile section | 17-18 | Not Started
39 |  | HTML: Doctor Management page | Table + add/edit/delete/search controls | 18 | Not Started
40 |  | HTML: Patient Management page | Table + add/edit/delete/search controls | 18 | Not Started
41 |  | HTML: Appointment Management page | Table + search, filter by status, update status | 19 | Not Started
42 |  | HTML: Department Management page | Table + add/edit/delete controls | 19 | Not Started
43 |  | Statistics cards | Total Doctors, Total Patients, Total Appointments, Department statistics | 19 | Not Started
44 |  | CSS: dashboard styling | Dashboard layout, sidebar, responsive tables, cards, buttons, forms - professional admin UI | 20 | Not Started
45 |  | JS: Doctor CRUD (Local Storage) | View, Add, Edit, Delete, Search doctors | 21 | Not Started
46 |  | JS: Patient CRUD (Local Storage) | View, Add, Edit, Delete, Search patients | 21 | Not Started
47 |  | JS: Appointment management | View, search, filter by status, update appointment status | 22 | Not Started
48 |  | JS: Department CRUD | View, Add, Edit, Delete departments | 22 | Not Started
49 |  | JS: dynamic statistics & tables | Dynamic dashboard stats, filtering, table manipulation, form validation | 23 | Not Started
50 |  | Responsive design check | Mobile, tablet, desktop responsive dashboard | 23 | Not Started
51 |  | Test & debug | Verify CRUD, responsiveness, forms, cross-browser; fix UI/functionality issues | 23 | Not Started
52 |  | Push Task 3 to GitHub | Commit into the Task 3 folder | 24 | Not Started
53 |  | Write Task 3 development report | Document in the Google Doc | 24 | Not Started
54 |  | Record demo video | Dashboard demonstration | 24 | Not Started
55 | 4 · Major Project - Healthcare / Clinic Management System | Auth: registration & login | Secure sign-up/login; separate login for Patient, Doctor, Admin | 25-26 | Not Started
56 |  | Auth: role-based access control | Role-based authentication and authorization; auth middleware | 26 | Not Started
57 |  | Frontend: core pages (HTML/CSS) | Home, Login/Register, Patient/Doctor/Admin dashboards, Appointment, Department, Contact - responsive | 27-29 | Not Started
58 |  | Backend: server + secure sessions | Node.js/PHP; secure session & token management | 30 | Not Started
59 |  | Backend: database + relationships | Relational DB, table relationships, connect application | 30-31 | Not Started
60 |  | Backend: RESTful API + CRUD | REST API endpoints; full CRUD operations | 31-32 | Not Started
61 |  | Backend: security | Password hashing/encryption, input validation, error handling | 32 | Not Started
62 |  | Patient Dashboard | View/update profile, book appointments, appointment history, medical records, notifications | 33 | Not Started
63 |  | Doctor Dashboard | Manage appointments & schedule, view patient details, update consultation status, manage profile | 34 | Not Started
64 |  | Admin Dashboard | Manage patients/doctors/departments/appointments, statistics, reports & analytics | 35 | Not Started
65 |  | Department management | Create/manage departments, assign doctors, department-wise listings | 36 | Not Started
66 |  | Appointment management | Book / reschedule / cancel; appointment status management | 36 | Not Started
67 |  | Notification management | Email notifications (demo), appointment reminders, status updates | 37 | Not Started
68 |  | Profile management | Update profile, change password, upload profile picture | 37 | Not Started
69 |  | Search & reports | Global search, export reports (CSV/PDF), dashboard analytics | 38 | Not Started
70 |  | JS: dynamic features | Dynamic booking, dashboard interactions, search/filter, statistics cards, role-based nav, charts (optional) | 38 | Not Started
71 |  | File upload support (optional) | Enable file/image uploads where relevant | 38 | Not Started
72 |  | Test & debug all modules | Auth, CRUD, responsiveness, cross-browser; fix identified bugs | 39 | Not Started
73 |  | Deployment (optional) | Prepare for deployment, configure env variables, deploy frontend & backend, verify functionality | 39 | Not Started
74 |  | Push Major Project to GitHub | Commit into the Major Project folder with proper documentation | 40 | Not Started
75 |  | Write project development report | System architecture, database design, methodology, challenges, solutions | 40 | Not Started
76 |  | Prepare project documentation in Google Doc, Upload in GitHub | Installation steps, project structure, database schema, API docs, future enhancements | 40 | Not Started
77 |  | Record project demo video, upload in GitHub | Features, responsiveness, overall workflow | 40 | Not Started
78 |  | Submit Intern Checklist, upload to GitHub | overall workflow | 40 | Not Started

## Key Rules
Key Rules & Reminders — iNeuBytes VIIP (WBINB20726)
• Tasks: 3 micro-assessment tasks (Landing Page, Booking System, Management Dashboard) + 1 Major Project (full Management System).
• Naming: GitHub repo name AND Google Doc title must be: InternFirstName_RegdNo_iNeuBytes
• Identity: README file and Google Doc main page must show Name, Regd No., and Course ID.
• Visibility: Keep the GitHub repo PUBLIC. Share links ONLY inside the iNeuBytes portal.
• Deadline: Submit all links in the portal (Task Submission) BEFORE 45 days.
• Word count: The Google Doc must meet the required word count (see program instructions).
• P1 review: After submission, expect a mandatory P1 Verification meeting (one-on-one or group).
• If rejected: Rework mentor comments and resubmit in P1 within the mentor's timeline. Mentor comments are final.
• P2 / LinkedIn: After approval, post on LinkedIn (tag iNeuBytes, add snippets + experience), use #ineubytes #ineubytesinternship, then share that post link in the portal.
• Do NOT: Share work links on social media / with third parties before completion (plagiarism & reassignment risk).
• Meetings: 1-hour sessions are mandatory; missing them can terminate the internship. Check email regularly.
• Prohibited: Copying from the internet, plagiarism, unpermitted AI use, disrespecting staff/policies.
• Support: If removed from the group without notice, email support@ineubytes.com immediately.